BusductTherMo — Edge Readiness for Cloud Integration

Detailed Work Steps for AWS Integration with a Cloud-Agnostic Architecture

Prepared for: Brahmadeo Kamble, Head of Digital & Industry 4.0, Godrej  |  Version 1.0 (Draft)  |  July 2026

# 1. Purpose and Scope

This document defines the engineering work required to prepare the BusductTherMo edge node (currently a self-contained system performing data collection, KPI computation, alarming, notification and historian functions) for integration with a cloud platform. The initial target platform is AWS; however, every design decision below is made so that the edge software can be repointed to Azure, GCP, or a private MQTT broker with configuration changes and a thin adapter swap — not a rewrite.

In scope: edge software restructuring, device identity, MQTT topic design, publish policy, offline buffering, remote configuration, and over-the-air (OTA) update readiness. Out of scope: cloud-side services (rules, storage tiering, dashboards), which are covered separately.

# 2. Cloud-Agnostic Design Principles

The following principles govern all work steps. They ensure AWS is a deployment choice, not an architectural dependency.

- Standards only at the wire level: MQTT 3.1.1/5.0 over TLS 1.2+ with X.509 client certificates. Every major cloud IoT platform and every self-hosted broker (EMQX, HiveMQ, Mosquitto) supports this profile.

- Provider adapter pattern: all cloud-specific behaviour (endpoints, provisioning API, shadow/twin semantics, OTA job APIs) is isolated in one replaceable module behind an internal interface. Core logic never imports a cloud SDK directly.

- Configuration over code: endpoints, topic templates, batch intervals and buffer limits live in the edge configuration file (busduct_edge_config.yaml), never hardcoded.

- Neutral payloads: JSON (optionally CBOR later) with self-describing fields and ISO-8601/epoch UTC timestamps generated at the edge. No provider-specific envelope formats in the payload.

- Generic config channel first: remote configuration is implemented as a plain cmd/ack topic pair. The AWS Device Shadow is supported as an optional optimisation inside the AWS adapter — the device twin concept exists on Azure too, but the generic channel is what guarantees portability.

- Edge autonomy is preserved: alarming, persistence logic and local historian continue to work with zero cloud connectivity. The cloud is an observer and configurator, never in the safety loop.

# 3. Target Edge Software Architecture

Restructure the edge application into the following layers before any cloud connectivity is added:

| Layer | Responsibility | Cloud dependency |
| --- | --- | --- |
| Acquisition & KPI engine | Sensor polling, ΔT and Rate-of-Rise computation, threshold and persistence evaluation, alarm state machine (Raise/Clear/ACK). | None |
| Local services | Historian (full resolution), alarm history, audit trail, local HMI/dashboard. | None |
| Message composer | Builds neutral JSON payloads: batched telemetry aggregates, alarm event snapshots, heartbeats. Applies size budget (<5 KB). | None |
| Store-and-forward queue | Disk-backed outbox with priority classes (alarms never dropped) and drain control. | None |
| Transport abstraction (interface) | publish(topic, payload, qos), subscribe(topic, handler), connection state events. | None |
| Provider adapter (AWS first) | Implements the transport interface: endpoint, TLS/cert handling, Basic Ingest topic mapping, optional Shadow sync, Fleet Provisioning, IoT Jobs for OTA. | Isolated here only |

The provider adapter is the only component replaced when changing cloud vendors. Everything above it is provider-neutral by construction.

# 4. Detailed Work Steps

## Phase 0 — Baseline Assessment and Refactoring (Week 1)

- Inventory the current edge codebase: identify where acquisition, alarm logic, notification, and historian functions are coupled. Document all points that would need to publish or receive data externally.

- Define the internal transport interface (publish/subscribe/connection-state) and refactor existing internal messaging to use it, with a loopback implementation so behaviour is unchanged.

- Freeze a regression baseline: record 1–2 weeks of alarm behaviour, KPI values and historian output from a reference panel. This becomes the acceptance benchmark for every later phase.

- Confirm hardware headroom on the edge device (CPU, RAM, flash endurance) for TLS, queueing and OTA. Define minimum spec for future units.

## Phase 1 — Device Identity and Provisioning (Weeks 1–2)

- Define the identity model: customer_id, site_id, panel_id (short immutable codes) plus hardware serial. Bake into the edge config at commissioning; treat as immutable thereafter.

- Generate a unique X.509 device certificate and private key per panel. Keys are generated on-device where hardware allows (never leave the device); otherwise use a controlled provisioning station.

- Implement certificate storage with restricted file permissions; plan for a secure element (ATECC608 or TPM) on future hardware revisions.

- Build the commissioning workflow for field technicians: enter identifiers, trigger provisioning, verify connectivity — one guided procedure, no manual cloud console steps.

- AWS adapter task: implement Fleet Provisioning (claim certificate exchanged for a unique operational certificate). Keep this entirely inside the adapter — Azure DPS or a custom PKI enrolment can replace it later.

- Implement certificate rotation support from day one: the device must accept a new certificate pushed via the config/OTA channel and switch atomically with rollback.

## Phase 2 — MQTT Client and Topic Structure (Weeks 2–3)

- Integrate a standards-based MQTT client library (e.g., Eclipse Paho or equivalent for your runtime). Do not use the AWS IoT Device SDK in core code; if used at all, wrap it inside the AWS adapter.

- Implement the topic hierarchy from configuration templates: dt/{customer}/{site}/{panel}/tel, .../alarm, and cmd/{customer}/{site}/{panel}/config with /ack. Resolve identifiers at startup.

- Configure TLS 1.2+ mutual authentication, long keep-alive (300 s) and jittered exponential reconnect backoff (2 s to 300 s).

- Implement Last Will and Testament (LWT) on the connection so the cloud can mark a panel offline immediately on ungraceful disconnect — this is standard MQTT and fully portable.

- AWS adapter task: optional mapping of the telemetry topic onto Basic Ingest ($aws/rules/...) for messaging-cost savings. The core code publishes to the logical topic; the adapter rewrites it. On another provider the adapter simply passes the topic through.

## Phase 3 — Publish Policy: Batching and Alarm Events (Weeks 3–4)

- Implement telemetry aggregation: per configurable interval (default 10 min), compute min/max/avg ΔT, max RoR and max temperature per joint, plus ambient, and publish one JSON message per panel at QoS 0.

- Enforce a payload size budget (default 4,800 bytes) with automatic key-shortening; log a warning if a payload ever exceeds the budget.

- Implement alarm event publishing on state transition only (RAISE, CLEAR, ACK) at QoS 1, carrying joint, level, KPI, value, threshold and persistence context.

- Implement a lightweight heartbeat (hourly) so the cloud distinguishes a quiet panel from a dead one.

- Validate against the Phase 0 baseline: cloud-received alarm sequence must match local alarm history exactly; aggregate telemetry must reconcile with the local historian.

## Phase 4 — Store-and-Forward Resilience (Weeks 4–5)

- Implement a disk-backed outbox with two priority classes: alarms (never dropped) and telemetry (drop-oldest on overflow). Default cap 200 MB.

- Stamp every payload with edge UTC event time; the cloud must never rely on broker receive time.

- Implement controlled drain on reconnect (default 5 msg/s) to avoid reconnection storms after a site-wide outage.

- Test systematically: pull the network for 1 hour, 24 hours, and 7 days; verify ordering, no alarm loss, correct timestamps, and graceful queue overflow behaviour.

## Phase 5 — Remote Configuration with Local Validation (Weeks 5–6)

- Implement the generic config channel: subscribe to cmd/.../config, apply, and respond on cmd/.../config/ack with applied version or rejection reason.

- Enforce local validation before apply: threshold ranges and ordering (Watch < Warning < Critical), RoR time-window limits, persistence-time ordering. The edge is the final authority on safety-relevant limits.

- Apply configuration atomically with a version number; reject stale or duplicate versions; keep last-known-good for corrupt-config recovery at boot.

- Write every remote change into the existing BusbarTherm audit trail (before/after, source, timestamp) so the current audit capability extends seamlessly to remote changes.

- AWS adapter task (optional): mirror the same config state through the Device Shadow for offline-sync convenience. The shadow is an optimisation; the cmd/ack channel remains the portable contract.

## Phase 6 — OTA Update Readiness (Weeks 6–8)

- Implement an A/B (dual-bank) update scheme or equivalent with automatic rollback on failed boot or failed health check.

- Require signed update packages; verify the signature on-device before applying. Keep the signing infrastructure provider-neutral (plain code-signing keys, not a cloud-proprietary format).

- Define the update trigger as a generic job message on the cmd channel (package URL + hash + signature). AWS adapter maps this to AWS IoT Jobs; other providers map to their equivalent or a plain HTTPS pull.

- Stagger rollouts: never update all panels of a site simultaneously; verify one panel's health before proceeding.

## Phase 7 — Pilot, Parallel Run and Rollout (Weeks 8–12)

- Retrofit one production panel end-to-end (Phases 1–5) and run it in parallel with the unchanged local system for at least 3–4 weeks.

- Compare daily: alarm-for-alarm parity with local history, telemetry reconciliation, MQTT message counts versus cost model, buffer behaviour during real network events.

- Run a portability drill before scaling: point the pilot panel at a local Mosquitto/EMQX broker using only configuration changes and the generic adapter. If anything breaks, a hidden AWS dependency has leaked into core code — fix it now, not after 50 sites.

- Template the validated configuration and commissioning procedure; then scale site by site.

# 5. Portability Decision Summary

| Capability | Portable mechanism (core) | AWS-specific optimisation (adapter only) |
| --- | --- | --- |
| Connectivity | MQTT 3.1.1/5.0 + TLS 1.2 + X.509 mutual auth | AWS IoT Core endpoint |
| Telemetry ingest | Plain topic dt/{c}/{s}/{p}/tel | Basic Ingest topic rewrite for cost |
| Offline detection | MQTT LWT + hourly heartbeat | AWS lifecycle events |
| Remote config | cmd/config + cmd/config/ack with versioning | Device Shadow mirror |
| Provisioning | X.509 enrolment workflow (PKI) | Fleet Provisioning API |
| OTA updates | Signed package + generic job message | AWS IoT Jobs orchestration |
| Payload format | Neutral JSON, edge UTC timestamps | None required |

Rule of thumb: if a feature appears in the right-hand column, it must live only inside the provider adapter and be removable without touching core logic.

# 6. Acceptance Criteria (Exit Checklist)

- Alarm parity: 100% match between cloud-received alarm events and local alarm history over the full pilot period.

- Autonomy: with the network disconnected for 7 days, local alarming, HMI and historian operate unaffected; on reconnect, all alarm events arrive with correct edge timestamps.

- Cost: measured MQTT message volume per panel per day is within the agreed budget (batched telemetry + event-driven alarms + heartbeat only).

- Safety of remote config: invalid or mis-ordered thresholds pushed from the cloud are rejected by the edge and reported on the ack channel; audit trail records every accepted change.

- Portability drill passed: the panel connects and operates against a non-AWS broker via configuration change only.

- OTA: a signed update applies successfully and a corrupted update rolls back automatically.

# 7. Key Risks and Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Cloud SDK usage leaks into core code | Vendor lock-in; costly rework at provider change | Adapter-only rule enforced in code review; portability drill in Phase 7 |
| Certificate/key compromise at commissioning | Device impersonation | On-device key generation, rotation support, per-device least-privilege policy |
| Reconnection storms after site outage | Broker throttling, delayed alarms | Jittered backoff + controlled outbox drain rate |
| Bad config push weakens alarm thresholds | Missed thermal faults | Edge-side validation rules and atomic apply; audit trail |
| Flash wear from queue writes on long outages | Edge hardware failure | Size-capped outbox, wear-aware write strategy, hardware headroom check in Phase 0 |